## Ledger
|  |  | Intechnic Corporation | [7 empty] | 451.5 | 320 | Week 3 | 12.01.2009 - 18.01-2009 | [6 empty] | 120 | 272 | Week 4 | 19.01.2009 - 25.01.2009 | [5 empty] | 120 | 280 | Week 5 | 26.01.2009 - 01.02.2009 | [5 empty] | 120 | 280 | Week 6 | 02.01.2009 - 08.02.2009 | [5 empty] | 120 | 280 | Week 7 | 09.01.2009 - 15.02.2009 | [5 empty] | 120 | 176 | Week 8 | 09.01.2009 - 15.02.2009 | [5 empty] | 16 | 170 | Week 9 | 23.02.2009 - 28.02.2009 | [5 empty] | 122 | 280 | Week 10 | 02.03.2009 - 08.03.2009 | [5 empty] | 120 | 256 | Week 11 | 03.09.2009 - 03.16.2009 | [5 empty] | 96 | 280 | Week 12 | 16.03.2009 - 22.03.2009 | [5 empty] | 120 | 272 | Week 13 | 23.03.2009 - 29.03.2009 | [5 empty] | 120 | 280 | Week 14 | 30.03.2009 - 05.04.2009 | [5 empty] | 120 | 228 | Week 15 | 06.04.2009 - 12.04.2009 | [5 empty] | 100 | 224 | Week 16 | 13.04.2009 - 19.04.2009 | [5 empty] | 96
Settings |  |  | Development Schedule |  |  |  |  | Average Eff. |  | 345.5 | 106 | 287 | 33 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 40 | 230 | 42 | 0 | 32 | 40 | 40 | 40 | 40 | 40 | 244 | 36 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 274 | 6 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 216 | 64 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 149 | 27 | 0 | 40 | 40 | 40 | 0 | 8 | 8 | 141 | 29 | 0 | 32 | 40 | 40 | 40 | 40 | 42 | 270 | 10 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 252 | 4 | 0 | 40 | 40 | 40 | 40 | 16 | 40 | 265 | 15 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 239 | 33 | 0 | 40 | 32 | 40 | 40 | 40 | 40 | 246 | 34 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 191 | 37 | 0 | 32 | 32 | 32 | 32 | 36 | 32 | 193 | 31 | 0 | 32 | 32 | 32 | 32 | 32 | 32
PMs | DMs | Cat | Type | PM | DM | Category | Company | Project | Status | Reserv | Req. | Reserv | Req. | Slava | Eric S | Gleb | Nikita F | Sergey | Alex | Denis | Grisha | Reserv | Req. | Slava | Eric S | Gleb | Nikita F | Sergey | Alex | Grisha | Reserv | Req. | Slava | Eric S | Gleb | Nikita F | Sergey | Alex | Grisha | Reserv | Req. | Slava | Eric S | Gleb | Nikita F | Sergey | Alex | Grisha | Reserv | Req. | Slava | Eric S | Gleb | Nikita F | Sergey | Alex | Grisha | Reserv | Req. | Slava | Eric S | Gleb | Nikita F | Sergey | Alex | Grisha | Reserv | Req. | Slava | Eric S | Gleb | Nikita F | Sergey | Alex | Grisha | Reserv | Req. | Slava | Eric S | Gleb | Nikita F | Sergey | Alex | Grisha | Reserv | Req. | Slava | Eric S | Gleb | Nikita F | Sergey | Alex | Grisha | Reserv | Req. | Slava | Eric S | Gleb | Nikita F | Sergey | Alex | Grisha | Reserv | Req. | Slava | Eric S | Gleb | Nikita F | Sergey | Alex | Grisha | Reserv | Req. | Slava | Eric S | Gleb | Nikita F | Sergey | Alex | Grisha | Reserv | Req. | Slava | Eric S | Gleb | Nikita F | Sergey | Alex | Grisha | Reserv | Req. | Slava | Eric S | Gleb | Nikita F | Sergey | Alex | Grisha
VG | KT | Manage | US | GA | GF | Develop | .NET obucheniye |  | active
US | VC | Promotion | US | PKO | SV | Develop | 3rd Millenium | website | active
Us | DA | Develop | US | GA | GK | Develop | AAAC | website | active
PV | SV | Slice-Up | US | GA | VC | Design | AAAC | website | active
PKO | FS | Design | US | GA | FS | Slice-Up | AAAC | website | active
PKH | VG |  | US | PKO | SV | Develop | Able | abledicasting | active
LV | GK |  | LV | PV | SV | Develop | ACG | In-Portal customization | closed
LV |  |  | LV | PV | GK | Develop | ACG | website | closed
l |  |  | LV | PV | FS | Slice-Up | ACG | website | closed
KT |  |  | LV | PV | VC | Design | ACG | website | closed
IV | SG |  | US | PKO | GK | Develop | ADN | website | active
GA |  |  | US | PKO | FS | Slice-Up | ADN | website | active
DA |  |  | US | GA | GF | Develop | ADN | website | active | 4
AN |  |  | US | GA | SV | Develop | AHP1 | website | active
AK |  |  | US | GA | VC | Design | AHP1 | website | active
KK |  |  | US | GA | GK | Develop | AHP1 | website | active
|  |  | US | GA | FS | Slice-Up | AHP1 | website | active
|  |  | US | PKO | KT | Develop | Alberto Roig | In-Portal customization | active
|  |  | LV | PV | GK | Develop | Aller | website | closed
|  |  | LV | PV | VC | Design | Aller | print materials | closed
|  |  | LV | PV | GK | Develop | Aller | website | closed
|  |  | LV | PV | FS | Slice-Up | Aller | website | closed
|  |  | US | AN | SV | Develop | Alloc | website | active
|  |  | US | AN | VC | Design | Alloc | website | active
|  |  | US | AN | FS | Slice-Up | Alloc | website | active
|  |  | LV | PV | VC | Design | Alton | website | closed
|  |  | LV | PV | GK | Develop | Alton | website | closed
|  |  | LV | PV | FS | Slice-Up | Alton | website | closed
|  |  | LV | PV | VC | Design | Alton | website | closed
|  |  | US | GA | SV | Develop | AMI | website | active
|  |  | US | GA | VC | Design | AMI | redesign | active
|  |  | US | GA | FS | Slice-Up | AMI | website | active
|  |  | LV | PV | SV | Develop | Antarts | In-Portal customization | closed
|  |  | LV | PV | FS | Slice-Up | Antarts | In-Portal customization | closed
|  |  | LV | PV | VC | Design | Antarts | website | closed
|  |  | LV | KT | SG | Develop | AON | website | active | [66 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0
|  |  | US | PKO | SV | Develop | Apex Jewels | website | active
|  |  | US | PKO | FS | Slice-Up | Apex Jewels | website | active
|  |  | US | IB | GK | Develop | Apex Wood Floors | website | active
|  |  | US | IB | FS | Slice-Up | Apex Wood Floors | website | active
|  |  | LV | PV | SG | Develop | APFH | website | closed
|  |  | LV | PV | FS | Slice-Up | APFH | website | active
|  |  | LV | PV | VC | Design | APFH | website | active
|  |  | LV | KT | VC | Design | ArbOOz | website | active |  | 6
|  |  | LV | KT | FS | Slice-Up | ArbOOz | website | active
|  |  | LV | KT | SG | Develop | Arbuz | website | active | 8 | [65 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0
|  |  | LV | KT | FS | Slice-Up | Arbuz | website | active |  | 1
|  |  | LV | KT | VC | Design | Arbuz | website | active
|  |  | US | PKO | GK | Develop | Atkins Gift Baskets | website | active
|  |  | LV | KT | SG | Develop | Auction | website | active | [12 empty] | 15 | [6 empty] | 15 |  | 11 | [6 empty] | 11 |  | 12 | [6 empty] | 12 |  | 10 | [6 empty] | 10 | [17 empty] | 8 |  | 4 | [6 empty] | 4 |  | 8 | [6 empty] | 8 |  | 2 | [6 empty] | 2 |  | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0
|  |  | LV | PV | VC | Design | Austrumu Expresis | website | active
|  |  | US | AN | GK | Develop | AWF | website | active
|  |  | US | AN | VC | Design | AWF | website | active
|  |  | US | AN | FS | Slice-Up | AWF | website | active
|  |  | US | AK | VC | Design | Ballonlady | website | active
|  |  | LV | KK | SG | Develop | Baltikums | website | active | [12 empty] | 10 | [5 empty] | 10 |  |  | 8 | [5 empty] | 8 | [38 empty] | 10 | [5 empty] | 10 |  |  | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0
|  |  | LV | PV | FS | Slice-Up | Baltikums | website | active
|  |  | LV | PV | VC | Design | Baltikums | website | active
|  |  | LV | PV | SG | Develop | BBCorporate (Baltikums) | website | closed
|  |  | LV | PV | FS | Slice-Up | BBCorporate (Baltikums) | website | active
|  |  | US | AN | GK | Develop | BBM | website | active
|  |  | US | AN | FS | Slice-Up | BBM (awf) | website | active
|  |  | LV | PV | VC | Design | Bcmukusala.lv | website | closed
|  |  | LV | PV | SG | Develop | Begonija | website | closed
|  |  | LV | PV | FS | Slice-Up | Begonija | website | active
|  |  | LV | PV | VC | Design | Begonija | website | active
|  |  | LV | KT | SG | Develop | Begonija ASU | website | active |  |  | 28 | [5 empty] | 12 | 16 |  |  | 24 | [5 empty] | 12 | 12 |  | 20 | [5 empty] | 12 | 8 |  | 23 | [5 empty] | 15 | 8 |  | 25 | [5 empty] | 15 | 10 | [16 empty] | 16 | 16 | 16 | 22 | [5 empty] | 6 | 16 |  | 28 | [5 empty] | 20 | 8 |  | 12 | [5 empty] | 6 | 6 |  | 24 | [5 empty] | 12 | 12 |  | 24 | [5 empty] | 12 | 12 |  | 26 | [5 empty] | 10 | 16 |  | 20 | [5 empty] | 12 | 8
|  |  | LV | KT | LV | Develop | Begonjia ASU | website | closed
|  |  | US | AK | GK | Develop | Biologic | ACE web site | active
|  |  | US | AK | FS | Slice-Up | Biologic - ACE | website | active
|  |  | LV | PV | VC | Design | BKE-VSP | website | closed
|  |  | LV | PV | FS | Slice-Up | BKE-VSP | website | closed
|  |  | LV | PV | GK | Develop | BKI-VSP | website | closed
|  |  | US | GA | GK | Develop | Black and Decker | website | active
|  |  | US | GA | SV | Develop | Blanketholler | website | closed
|  |  | LV | KT | SG | Develop | BMA | website | active | [66 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 8 | [6 empty] | 8
|  |  | US | GA | SV | Develop | BMC | website | active
|  |  | US | GA | FS | Slice-Up | BMC | website | active
|  |  | US | GA | SV | Develop | Box Enclosures | website | active
|  |  | US | GA | FS | Slice-Up | Box Enclosures | website | active
|  |  | US | GA | GK | Develop | Brunswick | website | active | 12.5 |  | 12 |  |  |  | 12 | [6 empty] | 2 |  |  | 2 | [23 empty] | 10 |  |  | 10 | [14 empty] | 4 |  |  | 4 | [14 empty] | 4 |  |  | 4 | [5 empty] | 4 |  |  | 4 | [5 empty] | 6 |  |  | 6 | [5 empty] | 4 |  |  | 4
|  |  | US | GA | SV | Develop | Brunswick | website (flash) | active
|  |  | US | GA | VC | Design | Brunswick | website | active
|  |  | US | GA | FS | Slice-Up | Brunswick | website | active |  |  | 3 | 2 | [54 empty] | 8 | [7 empty] | 16 | [8 empty] | 5 | [9 empty] | 3 | [8 empty] | 4
|  |  | LV | PV | VC | Design | BT&T | website | closed
|  |  | LV | PV | VC | Design | BTK.LV | website | closed
|  |  | US | GA | SV | Develop | Buffos Hot Sause | website | closed
|  |  | LV | PV | VC | Design | BuilderLings | website | closed
|  |  | LV | KT | SG | Develop | Bum | website | closed
|  |  | LV | PV | FS | Slice-Up | Bum | website | active
|  |  | US | AK | GK | Develop | Buskro | website | active | [66 empty] | 3 |  |  |  | 3
|  |  | US | AK | VC | Design | Buskro | website | active
|  |  | US | GA | GF | Develop | Catalyst Exhibits | website | active
|  |  | US | MX | FS | Slice-Up | Catalyst Exhibits | website | active | [93 empty] | 4 | [27 empty] | 4
|  |  | US | MX | GK | Develop | Catalyst Exhibits | website | active | [13 empty] | 4 |  |  | 4 |  |  |  |  | 16 |  |  |  | 16 |  |  |  |  | 14 |  |  |  | 14 |  |  |  |  | 8 |  |  |  | 8 | [5 empty] | 8 |  |  | 8 | [5 empty] | 4 |  |  | 4 | [5 empty] | 2 |  |  | 2 |  |  |  |  | 4 |  |  |  | 4 | [5 empty] | 4 |  |  | 4 | [5 empty] | 6 |  |  | 6 | [22 empty] | 12 |  |  |  | 12
|  |  | US | MX | SV | Develop | Catalyst Exhibits | website | active
|  |  | US | PKH | GK | Develop | CBS | website | active
|  |  | LV | KK | SG | Develop | CEF | website | closed
|  |  | LV | PV | VC | Design | CEF | website | active
|  |  | LV | PV | LV | Develop | CEF | website | closed
|  |  | LV | KK | SG | Develop | CEF (findme) | website | active | [63 empty] | 4 |  |  | 0 | [8 empty] | 0 | [8 empty] | 4 | [5 empty] | 4 |  |  | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0
|  |  | LV | PV | FS | Slice-Up | CEF (findme) | website | active | [22 empty] | 8 | [7 empty] | 12 | [8 empty] | 8 | [18 empty] | 4 | [7 empty] | 2
|  |  | US | AK | GK | Develop | Chaney Co | website | active | [13 empty] | 2 |  |  |  | 2 |  |  |  |  | 3 |  |  |  | 3 |  |  |  | 2 |  |  |  |  | 2
|  |  | US | AK | FS | Slice-Up | Chaney Co | website | active
|  |  | US | AK | GK | Develop | Chicago Lawyers Comm | website | active
|  |  | US | AK | VC | Design | Chicago Lawyers Comm | website | active
|  |  | US | AK | FS | Slice-Up | Chicago Lawyers Comm | website | active
|  |  | US | PKO | SV | Develop | City Squares | In-Portal customization | active
|  |  | US | PKO | FS | Slice-Up | City Squares | website | active
|  |  | LV | KT | FS | Slice-Up | Colby | website | active
|  |  | LV | KT | SG | Develop | Colby | website | closed
|  |  | LV | PV | SG | Develop | Combifragt | website | closed
|  |  | US | PKO | GK | Develop | Conform 2 Scorm | In-Portal customization | active
|  |  | LV | PV | GK | Develop | Consul | website | closed
|  |  | US | GA | SV | Develop | Corley Land Services | website | active
|  |  | US | GA | VC | Design | Corley Land Services | website | active
|  |  | US | GA | FS | Slice-Up | Corley Land Services | website | active
|  |  | US | PKO | SV | Develop | Corner Blog | website | active
|  |  | US | AK | FS | Slice-Up | Corner Blog | website | active
|  |  | US | GA | VC | Design | CorvetteForum | website | active
|  |  | US | GA | GK | Develop | CorvetteForum | forum/website/all forums | active
|  |  | LV | PV | VC | Design | CTC | website | active
|  |  | LV | PV | FS | Slice-Up | CTC | website | active
|  |  | LV | KT | SG | Develop | CTC | website | active | [66 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0
|  |  | US | GA | FS | Slice-Up | Cuddl Duds | website | active
|  |  | US | GA | GK | Develop | Cuddl Duds | website | active | [40 empty] | 12 |  | 4 |  | 8 |  |  |  | 9 |  |  | 9
|  |  | US | PKO | FS | Slice-Up | Danfoss | website | active
|  |  | US | AN | FS | Slice-Up | David James Design | website | active
|  |  | US | GA | GK | Develop | DeliveryOptions | website | active | [13 empty] | 2 |  |  | 2
|  |  | US | GA | SV | Develop | DeliveryOptions | website | active
|  |  | US | GA | VC | Design | DeliveryOptions | website | active
|  |  | US | GA | FS | Slice-Up | DeliveryOptions | website | active
|  |  | US | AK | SV | Develop | Demo | Intechnic Demo Site | active
|  |  | LV | SG | FS | Slice-Up | DenisS | website | active | [93 empty] | 2 | [8 empty] | 2
|  |  | US | IB | FS | Slice-Up | Design Odyssey | website | active
|  |  | US | IB | GK | Slice-Up | Design Odyssey | website | active
|  |  | US | PKO | GK | Develop | DHL API | website | active
|  |  | US | PKO | FS | Slice-Up | DHL API | website | active
|  |  | US | PKO | VC | Design | DHL API | website | active
|  |  | US | GA | GK | Develop | DishBuy | website | active
|  |  | US | AK | FS | Slice-Up | Documentation | Intechnic | active
|  |  | US | GA | GK | Develop | EAI | website | active | [102 empty] | 1 |  |  |  | 1
|  |  | US | GA | SV | Develop | EAI | website | active
|  |  | US | GA | VC | Design | EAI | redesign | active
|  |  | US | GA | FS | Slice-Up | EAI | redesign | active
|  |  | US | GA | GK | Develop | Earthday | website | active | [93 empty] | 16 | 2 |  | 16 | 2 |  |  |  |  | 16 | 6 |  | 16 | 6 | [14 empty] | 4 |  |  | 4
|  |  | US | PKO | SV | Develop | Ebay | website | active
|  |  | US | AK | SV | Develop | E-bullpen | website | active
|  |  | US | AK | VC | Design | E-bullpen | website | active
|  |  | US | GA | FS | Slice-Up | E-bullpen | FreeLanceToday | active
|  |  | US | AK | FS | Slice-Up | E-bullpen | Amsource | active | [30 empty] | 8
|  |  | US | AK | FS | Slice-Up | E-bullpen | website | active
|  |  | US | AK | KT | Develop | E-bullpen | In-Portal customization | active
|  |  | US | AK | SV | Develop | E-bullpen | Amsource | active |  |  | 14 |  | 12 | 2
|  |  | US | GA | SV | Develop | E-bullpen | FreeLanceToday | active
|  |  | US | AK | SV | Develop | E-bullpen | Stockamp | active
|  |  | US | AK | GK | Develop | Edsey | website | active
|  |  | US | AK | FS | Slice-Up | Edsey | website | active
|  |  | LV | VG | VC | Design | eHealth | website | active
|  |  | LV | VG | SG | Develop | eHealth | website | closed
|  |  | LV | VG | FS | Slice-Up | eHealth | website | active
|  |  | LV | PV | VC | Design | EiropasApavi | website | active
|  |  | LV | PV | VC | Design | EiropasApavi | website | active
|  |  | LV | KT | SG | Develop | EiropasApavi | website | active | [66 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0
|  |  | LV | PV | LV | Develop | EiropasApavi | website | closed
|  |  | LV | PV | FS | Slice-Up | EiropasApavi | website | active
|  |  | US | GA | GK | Develop | Emerald Spa Corporation | website | active
|  |  | US | GA | GK | Develop | Entrata | eWedding & Bridalconcierge | active
|  |  | US | GA | VC | Design | Entrata | eWedding & Bridalconcierge | active
|  |  | US | GA | FS | Slice-Up | Entrata | eWedding & Bridalconcierge | active
|  |  | US | MX | GK | Develop | Esbec | website | active
|  |  | LV | PV | VC | Design | Essential | website | active
|  |  | LV | AI | VC | Design | Evermen | website | closed
|  |  | LV | PV | SV | Develop | Evermen | website | closed
|  |  | US | PKO | KT | Develop | Executive Alaska One | In-Portal customization | active
|  |  | US | PKO | FS | Slice-Up | Executive Alaska One | website | active
|  |  | US | GA | GK | Develop | Express1 | website | active
|  |  | US | AN | FS | Slice-Up | FBD | website | active
|  |  | LV | KT | SG | Develop | FelixGroup | website | active | [66 empty] | 6 | [5 empty] | 6 |  |  | 0 | [8 empty] | 4 | [7 empty] | 4 | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0
|  |  | US | PKO | SV | Develop | FinartMasters | remake | active
|  |  | US | PKO | VC | Design | FinartMasters | remake | active
|  |  | US | PKO | FS | Slice-Up | FinartMasters | website | active
|  |  | LV | PV | VC | Design | FindMe.lv | website | active
|  |  | US | PKO | SV | Develop | FlooringBD | website | active
|  |  | US | PKO | FS | Slice-Up | FlooringBD | website | active
|  |  | LV | DA | FS | Slice-Up | Franck N. | Franck's Incommerce Proejct | active
|  |  | US | GA | SV | Develop | Furniture Deals Direct | website | active
|  |  | US | GA | FS | Slice-Up | Furniture Deals Direct | website | active
|  |  | US | GA | GK | Design | Fuse Snowskate | website | active
|  |  | US | GA | SV | Develop | FXWB | website | active
|  |  | US | GA | GK | Develop | FXWB | FX prints | active
|  |  | US | GA | VC | Design | FXWB | FX prints | active
|  |  | US | GA | VC | Design | FXWB | Plans & Specs | active
|  |  | US | GA | GF | Develop | FXWB | Plans & Specs | active | 46 |  | 10 | [8 empty] | 10 | 5 | [7 empty] | 5 | 10 | [7 empty] | 10 | 8 | [7 empty] | 8 | 8 | [7 empty] | 8 | 8 | [7 empty] | 8 | 2 | [7 empty] | 2
|  |  | US | GA | FS | Slice-Up | Nlcprint.com | website | active | [75 empty] | 7
|  |  | US | PKO | SV | Develop | Gavi | website | active
|  |  | US | PKO | FS | Slice-Up | Gavi | website | active
|  |  | US | AK | VC | Design | Gershman Group | website | closed
|  |  | US | GA | VC | Design | GISi | website | active
|  |  | US | GA | GK | Develop | GISi | website | active
|  |  | US | GA | FS | Slice-Up | GISi | website | active
|  |  | US | PKO | SV | Develop | Global 1 Equity | website | active
|  |  | US | GA | GK | Develop | Global Choice Health | website | active |  |  |  | 9 |  |  |  | 9 |  |  |  |  | 16 |  |  |  |  | 16 | [12 empty] | 10 |  |  |  |  | 10 | [21 empty] | 10 |  |  |  | 2 | 8 | [31 empty] | 4 |  | 4
|  |  | US | PKO | SV | Develop | Global Talks | website | active
|  |  | US | PKO | FS | Slice-up | Global1One | website | active
|  |  | US | GA | FS | Slice-Up | Global Choice Health | website | active | [22 empty] | 6 | [7 empty] | 8 | [35 empty] | 4
|  |  | US | AK | SV | Develop | Gourmet | cc integration | active
|  |  | US | PKO | FS | Slice-Up | Grid1 | website | active |  |  | 4
|  |  | US | PKO | SV | Develop | Grid1 | In-Portal customization | active | 4 |  |  | 8 | 8
|  |  | US | PKO | VC | Design | Grid1 | website | active
|  |  | US | PKO | VC | Design | Hifiway | website | active
|  |  | US | PKO | FS | Slice-Up | Hifiway | website | active
|  |  | US | GA | SV | Develop | Hosting | Hosting | active
|  |  | US | PKO | KT | Develop | Hula Direct | website | active
|  |  | US | PKO | FS | Slice-Up | Hula Direct | website | active
|  |  | US | GA | VC | Design | Incobrasa | website | active
|  |  | US | GA | FS | Slice-Up | Incobrasa | website | active
|  |  | US | IB | SV | Develop | Incredibikes | website | active
|  |  | US | AK | VC | Design | INDFE | website | active
|  |  | US | GA | GK | Develop | INDFE | website | active
|  |  | LV | PV | FS | Slice-up | IngBP | website | active
|  |  | LV | PV | SG | Develop | IngBP | website | closed
|  |  | US | PKO | FS | Slice-Up | In-Portal Customization | website | active
|  |  | LV | PV | VC | Design | Intec | website | active
|  |  | US | AK | SV | Develop | Intechnic | Demo Site | active
|  |  | US | AK | SV | Develop | Intechnic | In-Business | active | 4
|  |  | US | AK | GK | Develop | Intechnic | Intechnic.com site | active | [21 empty] | 15 |  |  | 15 | [5 empty] | 18 |  |  | 18 | [6 empty] | 8 |  | 8 | [23 empty] | 8 |  |  | 8
|  |  | US | AK | VC | Design | Intechnic | Misc/Sales/Marketing | active
|  |  | US | AK | VC | Design | Intechnic | Demo Site | active
|  |  | US | AK | VC | Design | Intechnic | Hosting | active
|  |  | US | AK | VC | Design | Intechnic | Intechnic.com site | active |  | 8
|  |  | US | AK | VC | Design | Intechnic | Cards/Calendars | closed
|  |  | US | AK | GK | Design | Intechnic | Marketing | closed
|  |  | US | AK | FS | Slice-Up | Intechnic | Intechnic.com site | active | [21 empty] | 9 | [17 empty] | 8 | [8 empty] | 8 | [35 empty] | 2 | [18 empty] | 4
|  |  | US | AK | FS | Slice-Up | Intechnic | Demo Site | active
|  |  | US | AK | FS | Slice-Up | Intechnic | Documentation | active
|  |  | US | AK | FS | Slice-Up | Intechnic | In-Business | active
|  |  | US | GA | SV | Develop | Intechnic | Report | active
|  |  | US | GA | SV | Develop | Intechnic | Standartization | active
|  |  | US | GA | VC | Design | Intechnic | Standartization | active
|  |  | US | GA | VC | Design | Intechnic | Documentation | active
|  |  | US | GA | VC | Design | Intechnic | CMS Demo | closed
|  |  | US | GA | FS | Slice-Up | Intechnic | Standartization | active
|  |  | US | GA | FS | Slice-Up | Intechnic | Documentation | active
|  |  | US | GA | FS | Slice-Up | Intechnic | Action Script Research | active
|  |  | US | GA | KT | Develop | Intechnic | In-Portal customization | active
|  |  | LV | AK | FS | Slice-Up | Intechnic | Control Panel | active
|  |  | US | DA | FS | Slice-Up | Intechnic | Software | active | 4
|  |  | LV | DA | FS | Slice-Up | Intechnic | In-commerce | active | [22 empty] | 1
|  |  | LV | DA | KT | Software | Intechnic | In-commerce | active
|  |  | LV | DA | VC | Design | Intechnic | In-commerce | active
|  |  | US | DA | SV | Develop | Intechnic | Software | active | [12 empty] | 8 | [6 empty] | 8 |  | 8 | [6 empty] | 8
|  |  | LV | AK | AO | Develop | Intechnic | R&D | active | 25 |  | 8 | [5 empty] | 4 | 4 |  |  | 10 | [5 empty] | 5 | 5 |  | 13 | [5 empty] | 5 | 8 |  | 13 | [5 empty] | 5 | 8 |  | 13 | [5 empty] | 5 | 8 | [19 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0
|  |  | LV | KT | KT | Software | Intechnic | Training | closed
|  |  | LV | KT | KT | Software | Intechnic | Licensing | closed
|  |  | US | AK | GK | Develop | Intechnic | R&D | active | [120 empty] | 16 | [6 empty] | 16
|  |  | LV | PV | VC | Design | Intechnic | Intechnic.lv site | active
|  |  | LV | PV | SG | Develop | Intechnic | Intechnic.lv site | closed
|  |  | LV | PV | FS | Slice-Up | Intechnic | Intechnic.lv site | active
|  |  | US | DA | GK | Develop | Intechnic | Software | active | 15 | [29 empty] | 8 | [6 empty] | 8 |  | 8 | [6 empty] | 8 |  | 8 | [6 empty] | 8 |  | 16 | [6 empty] | 16 |  | 16 | [6 empty] | 16 | [10 empty] | 16 | [6 empty] | 16 |  | 16 | [6 empty] | 16 |  | 16 | [6 empty] | 16 |  | 16 | [6 empty] | 16
|  |  | US | MX | FS | Slice-Up | Ishoppingreview | website | active
|  |  | US | MX | SV | Develop | Ishoppingreview | website | active
|  |  | US | GA | GK | Develop | Janos | additions | active
|  |  | LV | PV | FS | Slice-Up | Jewel | website | closed
|  |  | LV | PV | GK | Develop | Jewel | website | closed
|  |  | LV | PV | VC | Design | Jewel | website | closed
|  |  | US | GA | VC | Design | Jewelry Site (WebNet) | website | active
|  |  | US | GA | GK | Develop | Jewelry Site (WebNet) | website | active |  | 1
|  |  | US | GA | FS | Slice-Up | Jewelry Site (WebNet) | website | active |  | 4
|  |  | US | GA | SV | Develop | Journal/Memoirs | website | active | 1
|  |  | US | GA | VC | Design | Journal/Memoirs | website | active
|  |  | US | PKO | GK | Develop | Jtraderz | website | active
|  |  | US | PKO | VC | Design | Jtraderz | website | active
|  |  | US | PKO | FS | Slice-Up | Jtraderz | website | active
|  |  | US | AN | SV | Develop | Justkids | website | active
|  |  | US | GA | SV | Develop | Kwizzical | website | active
|  |  | US | GA | VC | Design | Kwizzical | website | active
|  |  | US | GA | FS | Slice-Up | Kwizzical | website | active
|  |  | US | AN | SV | Develop | LakeForestMediaGRP | website | active
|  |  | US | AN | FS | Slice-Up | LakeForestMediaGRP | website | active | 7 | 4
|  |  | US | IB | GK | Develop | Laptopaid | website | active |  |  | 20 |  |  |  | 20 | [5 empty] | 16 |  |  |  | 16 |  |  |  |  | 20 |  |  | 16 | 4 |  |  |  |  | 20 |  |  | 18 | 2 |  |  |  |  | 22 |  |  | 16 | 6 | [22 empty] | 1 |  |  | 1 | [5 empty] | 2 |  |  | 2
|  |  | US | IB | SV | Develop | Laptopaid | website | active |  |  | 24 |  |  | 24 | [6 empty] | 21 |  |  | 21
|  |  | LV | PV | KT | Develop | Lat.lv | In-Portal customization | closed
|  |  | LV | PV | VC | Design | Lat.lv | website | closed
|  |  | LV | KT | SG | Develop | DenisS | website | active | [66 empty] | 0 | [8 empty] | 0 | [8 empty] | 12 | [6 empty] | 4 | 8 | 12 | [6 empty] | 4 | 8 | 4 | [6 empty] | 4 |  | 0 | [8 empty] | 0
|  |  | LV | KK | FS | Develop | Latnami | website | active | [66 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0
|  |  | US | GA | FS | Slice-Up | Lawyersincorporated | website | active
|  |  | US | GA | SV | Develop | Lawyersincorporated | website | active
|  |  | LV | PV | GK | Develop | Leax | accounting system | closed
|  |  | LV | PV | SG | Develop | LHF | website | closed
|  |  | US | GA | VC | Design | Living Voices | in-portal theme design | active
|  |  | US | GA | GK | Develop | Living Voices | website | active
|  |  | US | GA | FS | Slice-Up | Living Voices | website | active
|  |  | US | GA | KT | Develop | Living Voices | In-Portal customization | active
|  |  | LV | PV | SG | Develop | LKN | website | closed
|  |  | LV | PV | VC | Design | LNK | website | active
|  |  | LV | PV | FS | Slice-Up | LNK | website | active
|  |  | LV | PV | VC | Design | Logitec | website | active
|  |  | LV | PV | FS | Slice-Up | Logitec | website | active
|  |  | LV | PV | GK | Develop | Lori | system | closed
|  |  | LV | PV | FS | Slice-Up | Lori | website | closed
|  |  | US | GA | FS | Slice-Up | LowCarb | website | active
|  |  | US | -- | SV | Develop | Management | -- | active |  |  | 16 | 8 | 16 |  |  |  |  | 8
|  |  | US | -- | GK | Develop | Management | -- | active | 10 |  | 7 |  |  |  | 7 | [5 empty] | 8 |  |  |  | 8 |  |  |  |  | 7 |  |  |  | 7 |  |  |  |  | 8 |  |  |  | 8 |  |  |  |  | 8 |  |  |  | 8 |  |  |  |  | 8 |  |  |  | 8 |  |  |  |  | 8 |  |  |  | 8 |  |  |  |  | 8 |  |  |  | 8 |  |  |  |  | 6 |  |  |  | 6 |  |  |  |  | 8 |  |  |  | 8 |  |  |  |  | 5 |  |  |  | 5 |  |  |  |  | 8 |  |  |  | 8 |  |  |  |  | 6 |  |  |  | 6 |  |  |  |  | 6 |  |  |  | 6
|  |  | US | -- | FS | Slice-Up | Management | -- | active |  |  | 4 | [18 empty] | 4 | [17 empty] | 4 | [44 empty] | 4 | [17 empty] | 6 | [8 empty] | 4 | [8 empty] | 4
|  |  | LV | -- | VG | Develop | Management | -- | closed
|  |  | LV | -- | KT | Software | Management | -- | active
|  |  | US | -- | GF | Develop | Management | -- | active
|  |  | LV | PV | SG | Develop | Marshall | website | closed
|  |  | LV | PV | FS | Slice-Up | Marshall | website | active
|  |  | LV | PV | VC | Design | Marshall | website | active
|  |  | US | GA | GK | Develop | Mazzetta | website | active | [58 empty] | 9 |  | 9 | [6 empty] | 8 |  | 8 | [42 empty] | 8 |  | 6 | 2
|  |  | US | GA | FS | Slice-Up | Mazzetta | website | active | [102 empty] | 8
|  |  | US | PKO | FS | Slice-Up | MBA | Business plan | active
|  |  | US | PKO | SV | Develop | MBA | website | active
|  |  | US | PKO | VC | Design | MBA | website | active
|  |  | US | PKO | SV | Develop | MBGH | website | active
|  |  | US | PKO | FS | Slice-Up | MBGH | website | active
|  |  | US | AK | SV | Develop | Med Retreat | website | active
|  |  | US | AK | VC | Design | Med Retreat | website | active
|  |  | US | AN | SV | Develop | MedFund | website | active
|  |  | US | AK | GK | Develop | MedFund | website | active
|  |  | US | AN | FS | Slice-Up | MedFund | website | active
|  |  | US | AK | FS | Slice-Up | MedRetreat | website | active
|  |  | LV | PV | SV | Develop | Meeting.lv | website | closed
|  |  | US | PKO | SV | Develop | Melford | website | active
|  |  | US | IB | GK | Develop | MindsUnite | website | active | [48 empty] | 10 |  |  | 10 | [5 empty] | 2 |  |  | 2 | [5 empty] | 2 |  |  | 2 | [5 empty] | 4 |  |  | 4 | [32 empty] | 1 |  |  | 1 | [5 empty] | 1 |  |  | 1
|  |  | US | IB | FS | Slice-Up | MindsUnite | website | active | [93 empty] | 2
|  |  | US | AN | GK | Develop | Minichristmas | website | active
|  |  | US | AN | SV | Develop | Minichristmas | website | active
|  |  | US | PKO | GK | Develop | Mirabelle | website | active
|  |  | US | PKO | FS | Slice-Up | Mirabelle | website | active
|  |  | US | PKO | VC | Design | Mirabelle | website | active
|  |  | US | AK | VC | Design | Misc | CCC Flash | closed
|  |  | US | GA | SV | Develop | Misc. Inportal Quoting | In-Portal Customization | active
|  |  | LV | DA | LV | Develop | Mobiland | In-Portal customization | closed
|  |  | LV | KT | FS | Slice-Up | Mobiland | website | active
|  |  | LV | KT | SG | Develop | Mobiland | website | active | 16 | [65 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0
|  |  | US | GA | SV | Develop | Moebs | website | closed
|  |  | US | GA | GK | Develop | Mortenson | HR | active
|  |  | US | GA | VC | Design | Mortenson | HR | closed
|  |  | US | GA | FS | Slice-Up | Mortenson | website | active
|  |  | US | PV | SV | Develop | mortenson (camera) | image upload | active
|  |  | US | AN | SV | Develop | MTCUS | website | active
|  |  | US | AN | FS | Slice-Up | MTCUS | website | active
|  |  | US | AN | VC | Design | MTCUS | website | active
|  |  | US | GA | SV | Develop | MyBeadGirl | website | active
|  |  | US | GA | FS | Slice-Up | MyBeadGirl | website | active
|  |  | US | AK | VC | Design | MyIcePus | website | active
|  |  | US | AK | FS | Slice-Up | MyIcePus | website | active
|  |  | LV | PV | GK | Develop | Natalie | website | closed
|  |  | US | GA | SV | Develop | NBRC | In-Portal customization | active |  |  | 4 | 1 | 1 | 4 | [7 empty] | 2 |  | 2
|  |  | US | GA | FS | Slice-Up | NBRC | website | active
|  |  | US | PKO | GK | Develop | Neo-Call | In-Portal customization | active | 4
|  |  | US | PKO | GK | Develop | Neo-Call | customization | active
|  |  | US | PKO | FS | Slice-Up | Neo-Call | website | active
|  |  | US | PKO | KT | Develop | Neo-Call | In-Portal customization | active
|  |  | US | PKO | GK | Develop | New Wave Direct | website | active
|  |  | US | PKO | VC | Design | New Wave Direct | website | active
|  |  | US | PKO | FS | Slice-Up | New Wave Direct | website | active
|  |  | US | AK | VC | Design | NSP | website | active
|  |  | US | AK | GK | Develop | NSP | website | active
|  |  | US | AK | FS | Slice-Up | NSP | website | active
[7 empty] | NSP |  | closed
|  |  | US | IB | GK | Develop | Olympia | website | active | 8 | [56 empty] | 1 |  |  |  | 1 | [13 empty] | 2 |  |  |  | 2 |  |  |  |  | 5 |  |  |  | 5 | [31 empty] | 1 |  |  |  | 1
|  |  | US | IB | FS | Slice-Up | Olympia | website | active | 1 | [56 empty] | 3 | [17 empty] | 3
|  |  | US | GA | SV | Develop | OMBOW | In-Portal Customization | active
|  |  | US | GA | VC | Design | OMBOW | website | active
|  |  | US | GA | FS | Slice-Up | OMBOW | website | active
|  |  | US | GA | SV | Develop | OMBOW | In-Portal customization | active
|  |  | US | GA | FS | Slice-Up | OTS | website | active
|  |  | US | GA | KT | Develop | OTS | In-Portal customization | active
|  |  | LV | PV | GK | Develop | Parfume.lv | website | closed
|  |  | LV | PV | FS | Slice-Up | Parfume.lv | website | closed
|  |  | LV | PV | VC | Design | Parfume.lv | website | closed
|  |  | US | GA | GK | Develop | Pastime Programs | website | active |  |  | 7 | 1 | 1 | 7 | [7 empty] | 4 |  | 4 | [6 empty] | 8 |  | 8 | [6 empty] | 6 |  | 4 | 2 | [31 empty] | 2 |  |  | 2 | [15 empty] | 4 |  | 4 | [15 empty] | 1 |  | 1
|  |  | US | GA | FS | Slice-Up | Pastime Programs | website | active
|  |  | US | GA | GK | Develop | Pastime Programs | website | active | [40 empty] | 7 |  | 7 | [68 empty] | 3 | 2 |  | 5
|  |  | US | PKO | SV | Develop | Pawky | website | active | 7
|  |  | US | PKO | VC | Design | Pawky | website | active
|  |  | US | PKO | FS | Slice-Up | Pawky | website | active |  | 1
|  |  | US | MX | VC | Design | PennyDoc | website | active | 3
|  |  | US | IB | GK | Develop | PennyDoc | website | active | 30 | [65 empty] | 2 |  |  | 2 | [5 empty] | 10 |  |  | 10 | [5 empty] | 12 |  |  | 12 | [5 empty] | 3 |  |  | 3 | [5 empty] | 4 |  |  | 4
|  |  | US | MX | FS | Slice-Up | PennyDoc | website | active | 8.5 | 3
|  |  | US | GA | FS | Slice-Up | PlansandSpecs | website | active
|  |  | US | GA | GK | Develop | PlansandSpecs | website | active | [120 empty] | 4 | [7 empty] | 4
|  |  | LV | -- | VG | Develop | PM Time | N/A | closed
|  |  | US | AN | VC | Design | PMT | website | active
|  |  | US | AN | FS | Slice-Up | PMT | website | active | 0.5
|  |  | US | AN | SV | Develop | PMT | website | active | 30 | 9
|  |  | US | IB | FS | Slice-Up | Pokerchips | additions | active | [48 empty] | 4
|  |  | US | IB | GK | Develop | Pokerchips | website | active |  |  | 20 |  |  |  |  | 20 |  |  |  |  | 6 |  |  |  |  | 6 |  |  |  | 24 |  |  |  | 8 | 16 |  |  |  | 20 |  |  |  | 2 | 18 |  |  |  | 8 |  |  |  |  | 8 |  |  |  | 31 |  |  |  | 10 | 21 |  |  |  | 28 |  |  |  | 8 | 20 |  |  |  | 20 |  |  |  | 4 | 16 |  |  |  | 23 |  |  |  | 7 | 16 |  |  |  | 36 |  |  |  | 12 | 24 |  |  |  | 18 |  |  |  | 2 | 16 |  |  |  | 14 |  |  |  | 4 | 10 |  |  |  | 6 |  |  |  | 2 | 4 |  |  |  | 4 |  |  |  |  | 4
|  |  | US | PKO | SV | Develop | Progressive Secretary | website | active
|  |  | US | DA | SV | Develop | Prospectiva | In-Portal customization | active
|  |  | LV | PV | SV | Develop | Prospects | website | closed
|  |  | US | AN | SV | Develop | RAD | In-Portal customization | active
|  |  | US | AN | FS | Slice-Up | RAD | website | active
|  |  | US | AN | KT | Develop | RAD | In-Portal Customization | active
|  |  | LV | PV | FS | Slice-Up | Rameks | website | active
|  |  | US | PKO | SV | Develop | Rapsessions | website | active
|  |  | US | PKO | VC | Design | Rapsessions | website | active
|  |  | US | PKO | FS | Slice-Up | Rapsessions | website | active
|  |  | US | AK | VC | Design | Resumark | website | active
|  |  | US | AK | FS | Slice-Up | Resumark | website | active | 2 | [83 empty] | 4 | [35 empty] | 16
|  |  | US | AK | GK | Develop | Resumark | website | active | 26 | 20 | 6 |  |  |  |  | 6 |  |  |  |  | 6 |  |  |  |  | 6 |  |  |  |  | 10 |  |  |  | 10 |  |  |  | 14 |  |  |  | 4 | 10 |  |  |  |  | 14 |  |  | 4 | 10 |  |  |  | 15 | 9 |  | 9 | 5 | 10 |  |  |  | 30 |  |  | 20 | 5 | 5 |  |  |  | 44 |  |  | 16 | 16 | 12 |  |  |  | 47 |  |  | 19 | 12 | 16 |  |  |  | 24 |  |  | 8 | 6 | 10 |  |  |  | 32 |  |  | 8 | 8 | 16 |  |  |  | 44 |  |  | 16 | 8 | 20 |  |  |  | 44 |  |  | 16 | 8 | 20 |  |  |  | 38 |  |  | 16 | 6 | 16
|  |  | LV | PV | SG | Develop | RIBI | website | closed
|  |  | LV | PV | SG | Develop | RigaRE | website | closed
|  |  | LV | PV | FS | Slice-Up | RigaRE | website | active
|  |  | LV | PV | SG | Develop | RigaShop | rigashop | closed
|  |  | US | GA | SV | Develop | RingTones | website | active
|  |  | LV | PV | FS | Design | RNC | website | active
|  |  | LV | PV | SG | Develop | RNC | website | closed
|  |  | US | AK | FS | Slice-Up | Room Designer | website | active |  |  |  | 4 | [8 empty] | 12 | [8 empty] | 12 | [8 empty] | 12 | [8 empty] | 20 | [8 empty] | 24 | [8 empty] | 25 | [8 empty] | 18 | [8 empty] | 25 | [8 empty] | 25 | [8 empty] | 26 | [8 empty] | 20 | [8 empty] | 12 | [8 empty] | 8
|  |  | US | AK | GK | Develop | Room Designer | website | active |  |  | 4 |  |  |  |  | 4 |  |  |  |  | 10 |  |  |  | 5 | 5 |  |  |  | 14 |  |  |  | 4 | 10 |  |  |  | 8 |  |  |  | 8 |  |  |  |  | 6 |  |  |  | 2 | 4 |  |  |  | 16 |  |  |  | 8 | 8 |  |  |  | 12 |  |  |  | 6 | 6 |  |  |  | 12 |  |  |  | 6 | 6 |  |  |  | 11 |  |  |  | 4 | 7 |  |  |  | 5 |  |  |  |  | 5
|  |  | US | GA | SV | Develop | RoyalPalaces | shopping cart | closed
|  |  | US | GA | FS | Slice-Up | RPI | website | active | [94 empty] | 2
|  |  | US | GA | GK | Develop | RPI | website | active | 28 | [120 empty] | 8 |  | 8
|  |  | LV | PV | VC | Design | Samsung | website | active
|  |  | LV | PV | SG | Develop | Samsung | website | closed
|  |  | LV | PV | FS | Slice-Up | Samsung | website | active
|  |  | LV | PV | SG | Develop | Saphir | website | active |  | 24 | [64 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0
|  |  | LV | PV | FS | Slice-Up | Saphir | website | active
|  |  | LV | PV | VC | Design | Saphir | website | active
|  |  | US | PKO | KT | Develop | SEO Arsenal | website | active
|  |  | US | PKO | VC | Design | SEO Arsenal | website | active
|  |  | US | PKO | FS | Slice-Up | SEO Arsenal | website | active
|  |  | LV | KK | SG | Develop | SexyStyle | website | active | [21 empty] | 2 | [5 empty] | 2 |  |  | 4 | [6 empty] | 4 | [28 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0
|  |  | US | PKO | VC | Design | SMS/APF | website | active
|  |  | US | PKO | FS | Slice-Up | SMS/APF | website | active
|  |  | US | PKO | GK | Develop | SMS/APF | website | active | [111 empty] | 1 |  |  | 1
|  |  | US | GA | VC | Design | SNS | website | active
|  |  | US | GA | GK | Develop | SNS | website | active
|  |  | US | GA | FS | Slice-Up | SNS | website | active
|  |  | US | GA | SV | Develop | SNS | In-Portal customization | active
|  |  | US | MX | VC | Design | Sodick | website | active
|  |  | US | MX | FS | Slice-Up | Sodick | website | active | [12 empty] | 1 | [99 empty] | 2
|  |  | US | MX | GK | Develop | Sodick | website | active | [12 empty] | 1 |  |  |  | 1 | [22 empty] | 1 |  |  |  | 1 | [13 empty] | 1 |  |  |  | 1
|  |  | US | MX | VC | Design | Sodick | website | active
|  |  | US | GA | FS | Slice-Up | Sofa World | website | active | 4
|  |  | US | GA | SV | Develop | Sofa World | website | active | 12
|  |  | US | GA | VC | Design | Sofa World | website | active
|  |  | US | PKO | SV | Develop | SonLox | website | active
|  |  | US | PKO | VC | Design | SonLox | website | active
|  |  | LV | KK | SG | Develop | SP Legion | system | active | [21 empty] | 5 | [6 empty] | 5 | [37 empty] | 8 | [5 empty] | 8 |  |  | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0
|  |  | US | PKO | GK | Develop | Sumicarbide | website | active
|  |  | US | GA | SV | Develop | Sundowner-Corp | website | active
|  |  | US | PKO | FS | Develop | Sundowner-Corp | website | active
|  |  | US | GA | GK | Design | Sundowner-Corp | website | active | [112 empty] | 4 |  |  | 4
|  |  | US | GA | GK | Develop | T100.org | website | active
|  |  | US | AK | SV | Develop | Talent Pen | website | active
|  |  | US | GA | SV | Develop | Task Force | website | active
|  |  | LV | KT | SV | Develop | Technoland | website | closed | 1
|  |  | LV | KT | VC | Design | Technoland | design | closed
|  |  | LV | KT | FS | Slice-Up | Technoland | website | closed
|  |  | US | PKO | SV | Develop | Telestial | website | active
|  |  | US | PKO | KT | Develop | Telestial | website | active
|  |  | LV | KT | VC | Design | Tilts | website | active
|  |  | LV | KK | SG | Develop | Tilts | website | active |  |  | 24 | [5 empty] | 12 | 12 |  |  | 10 | [5 empty] | 10 |  |  | 13 | [5 empty] | 13 |  |  | 10 | [5 empty] | 10 |  |  | 10 | [5 empty] | 10 | [17 empty] | 10 |  |  | 30 | [5 empty] | 10 |  | 20 | 40 | [5 empty] | 20 |  | 20 | 48 | [5 empty] | 22 | 8 | 18 | 52 | [5 empty] | 20 | 8 | 24 | 58 | [5 empty] | 20 | 8 | 30 | 42 | [5 empty] | 16 | 4 | 22 | 32 | [5 empty] | 12 |  | 20
|  |  | LV | KT | LV | Develop | Tilts | website | closed | 8
|  |  | LV | KT | FS | Slice-Up | Tilts | website | active
|  |  | US | GA | SV | Develop | Tradexpro | In-Portal Customization | active |  | 2
|  |  | US | GA | VC | Design | Tradexpro | In-Portal Customization | active
|  |  | US | GA | FS | Slice-Up | Tradexpro | website | active
|  |  | US | GA | GK | Develop | Tradexpro | website | active
|  |  | US | PKO | GK | Develop | Trends | In-Portal customization | active
|  |  | US | PKO | SV | Develop | Trends | website | active
|  |  | US | PKO | VC | Design | Trends | website | active
|  |  | US | PKO | KT | Develop | Trends | In-Portal customization | active
|  |  | US | PKO | FS | Slice-Up | Trends | website | active
|  |  | US | GA | SV | Develop | TrustFX | website | active
|  |  | US | GA | VC | Design | TrustFX | Flash | active
|  |  | LV | KT | VC | Design | TTS | design | active
|  |  | LV | KK | SG | Develop | TTS | system | active | 24 |  | 42 | [5 empty] | 12 |  |  | 30 | 38 | [5 empty] | 3 |  | 35 | 30 | [7 empty] | 30 | 42 | [5 empty] | 10 |  | 32 | 42 | [5 empty] | 10 |  | 32 | [15 empty] | 10 |  | 24 | 20 | [7 empty] | 20 | 20 | [7 empty] | 20 | 16 | [5 empty] | 6 | 2 | 8 | 16 | [5 empty] | 8 |  | 8 | 18 | [5 empty] | 8 |  | 10 | 16 | [5 empty] | 6 |  | 10 | 16 | [5 empty] | 8 |  | 8
|  |  | LV | KT | FS | Slice-Up | TTS | website | active
|  |  | LV | -- | VG | Develop | Unplanned | -- | closed
|  |  | US | -- | SV | Develop | Unplanned / R&D | -- | active |  | 23 | 1 |  |  | 1 | [6 empty] | 1 |  |  | 1
|  |  | US | -- | GK | Develop | Unplanned / R&D | -- | active | 1 |  | 2 |  |  |  | 1 | 1 |  |  |  |  | 7 |  |  |  | 2 | 5 |  |  |  | 3 |  |  | 1 | 1 | 1 | [12 empty] | 3 | 9 |  | 1 | 1 | 10 |  |  |  | 3 |  |  | 1 | 1 | 1 |  |  |  | 3 |  |  | 1 | 1 | 1 |  |  |  | 8 |  |  | 1 | 1 | 6 |  |  |  | 3 |  |  | 1 | 1 | 1 |  |  |  | 3 |  |  | 1 | 1 | 1 |  |  |  | 3 | 7 |  | 1 | 1 | 8 |  |  |  | 3 | 15 |  | 1 | 7 | 10 |  |  |  | 3 | 7 |  | 1 | 1 | 8 |  |  |  | 3 | 15 |  | 5 | 1 | 12
|  |  | US | -- | FS | Slice-Up | Unplanned / R&D | -- | active |  |  | 23 | [9 empty] | 1 | 26 | [98 empty] | 14
|  |  | LV | -- | SG | Develop | Unplanned/Training | -- | active | [66 empty] | 0 | [8 empty] | 0 | [8 empty] | 6 | [5 empty] | 2 | 2 | 2 | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0
|  |  | US | GA | SV | Develop | UseekUfind | In-Portal Customization | active
|  |  | US | GA | VC | Design | UseekUfind | in-portal theme design | active
|  |  | US | GA | GK | Develop | UseekUfind | website | active
|  |  | US | GA | KT | Develop | UseekUfind | In-Portal customization | active
|  |  | US | AK | SV | Develop | Verist | website | active
|  |  | US | AK | VC | Design | Verist | website | active
|  |  | US | AK | FS | Slice-Up | Verist | website | active
|  |  | LV | PV | SG | Develop | Villa Blanca | website | closed
|  |  | LV | PV | FS | Slice-Up | Villa Blanca | website | active
|  |  | LV | PV | VC | Design | Villa Blanca | website | active
|  |  | US | GA | GK | Develop | Vogue Printing | website | active | [111 empty] | 7 |  |  |  | 7
|  |  | LV | KT | FS | Slice-Up | VP | website | closed
|  |  | LV | KK | SG | Develop | VP | website | active | [39 empty] | 4 | [6 empty] | 4 | [19 empty] | 4 | [6 empty] | 4 |  | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0
|  |  | US | GA | SV | Develop | Waterfowler | Chat Application | active
|  |  | US | GA | FS | Slice-Up | Waterfowler | website | active
|  |  | US | GA | KT | Develop | Waterfowler | In-Portal customization | active
|  |  | US | GA | GK | Develop | Waterfowler | website | active | [75 empty] | 4 |  |  | 4
|  |  | US | PKO | GK | Develop | Webcom 247 | In-Portal customization | active
|  |  | US | PKO | SV | Develop | Windy City Photo | website | active
|  |  | US | PKO | VC | Design | Windy City Photo | website | active
|  |  | US | PKO | FS | Slice-Up | Windy City Photo | website | active
|  |  | LV | PV | FS | Slice-Up | Worksafety | website | closed
|  |  | LV | PV | GK | Develop | Worksafety | website | closed
|  |  | LV | PV | VC | Design | Worksafety | website | closed
|  |  | US | GA | FS | Slice-Up | World Choice Healthcare | website | active | [48 empty] | 3
|  |  | US | GA | SV | Develop | World Choice Healthcare | website | active
|  |  | US | AK | FS | Slice-Up | World Equity Group | website | active | [48 empty] | 1 | [35 empty] | 2
|  |  | US | AK | GK | Develop | World Equity Group | website | active |  |  | 4 |  | 2 | 2 | [6 empty] | 4 |  |  | 4 | [24 empty] | 4 |  | 4 | [5 empty] | 1 | 10 |  | 11 | [32 empty] | 15 |  |  | 15 | [5 empty] | 8 | 2 |  | 8 | 2 | [5 empty] | 4 |  | 2 | 2 |  |  |  |  | 4 |  |  | 2 | 2 |  |  |  |  | 4 |  |  | 2 | 2
|  |  | LV | PV | GK | Develop | X-Net | website | closed
|  |  | LV | PV | FS | Slice-Up | X-Net | website | closed
|  |  | LV | PV | VC | Design | X-Net | website | closed
Note on EG1: Kostja: 4 Working Days!!! (10.04 - Easter)
Note on EQ1: Kostja: 4 Working Days!!! (13.04 - Easter)

## Teams
Slava | Projects
Slava | 0
0
Slice-Up
Stanislav | 32
32
Kostja | Products
Sergey
Dennis | 32
Alex | 32
Grigorij | 32
96
Gleb
Gleb | 32
Nikita F | 32
Eric S | 32
96
224

## Slava's Team
| Slava | Alexey | Eric S | Eric H | Alex | Nikita
Gourmet | x
Corner Blog | x |  |  | x
Demo | x |  |  | x
Med Retreat | x |  | x
Talent Pen | x | x |  | x
E-bullpen | x | x |  | x
Verist | x |  | x
In-Business | x |  | x
RAD |  |  |  |  | x
LakeForestMediaGRP | x |  |  | x |  | x
MTCUS | x |  |  | x
Alloc | x |  | x | x
Waterfowler (chat application only) | x
AHP1 | x | x | x | x | x | x
FXWB | x | x | x | x | x | x
Intechnic.com | x |  | x
Journal/Memoirs | x |  | x
EAI | x | x
RingTones | n/a | n/a | n/a | n/a | n/a | n/a
Kwizzical | x |  | x
AMI | n/a | n/a | n/a | n/a | n/a | n/a
TrustFX | n/a | n/a | n/a | n/a | n/a | n/a
BMC | x |  |  | x
Sundowner-Corp | x
Brunswick (flash only) |  | x
Furniture Deals Direct/Stone Marten | x |  | x | x
Corley Land Services | x |  |  | x |  | x
OMBOW |  |  |  |  | x
NBRC |  | x |  |  | x
DeliveryOptions (flash only) |  | x
UseekUfind |  |  |  |  | x
Tradexpro |  |  |  |  | x
Vogue Printing | x
Box Enclosures | x |  |  | x
Blanketholler | n/a | n/a | n/a | n/a | n/a | n/a
Moebs | n/a | n/a | n/a | n/a | n/a | n/a
RoyalPalaces | x | x | x | x | x | x
Buffos Hot Sause | n/a | n/a | n/a | n/a | n/a | n/a
Lawyersincorporated | x |  | x
SNS |  |  |  |  | x
Grid1 | x | x |  |  | x
FinartMasters | x |  | x
Neo-Call (flash only) |  | x
Able | x
Pokerchips | x
Melford | x | x
Gavi | x |  | x |  |  | x
RPI | x | x
Progressive Secretary | n/a | n/a | n/a | n/a | n/a | n/a
SMS/APF | x | x | x |  |  | x
Windy City Photo | x |  | x
FlooringBD | x |  | x
Pawky | x | x | x | x
SonLox | x | x
MBGH | n/a | n/a | n/a | n/a | n/a | n/a
Global Talks | n/a | n/a | n/a | n/a | n/a | n/a
MBA | x
Global 1 Equity | x | x
Rapsessions | x |  | x
City Squares |  |  |  |  | x
Prospectiva |  | x
Intechnic.lv | x | x | x
Tilts | x |  | x
ACG |  |  |  |  | x
Combifragt | x | x |  |  |  | x
Mobiland |  |  |  |  | x
Antarts |  |  |  |  | x
Samsung | x |  | x | x
Limon | x |  |  |  | x
Marshall | x |  | x
Mobiland |  |  |  |  | x
Note on B42: Gene: non In-portal only
Note on C19: Gene: flash only
Note on C42: Gene: In-portal Only
Note on F42: Gene: In-portal only

## Gleb's Team
| Gleb | Sergey | Denis | Maxim
Buskro | n/a | n/a | n/a | n/a
Chicago Lawyers Comm | x | x | x | x
AWF | x |  |  | x
DeliveryOptions | x
FXWB | x
Janos | x
Brunswick | x
Entrata | x
AAAC | n/a | n/a | n/a | n/a
Mortenson | x
CorvetteForum | x | x
INDFE | x | x | x | x
T100.org | n/a | n/a | n/a | n/a
Emerald Spa Corporation | x
Living Voices |  | x
GISi | x | x | x | x
DishBuy | n/a | n/a | n/a | n/a
Waterfowler |  | x
DHL API | x |  | x | x
Sumicarbide | n/a | n/a | n/a | n/a
Atkins Gift Baskets | n/a | n/a | n/a | n/a
Trends |  | x |  | x
Neo-Call |  | x
ADN | x |  |  | x
Sodick | x | x |  | x
New Wave Direct | n/a | n/a | n/a | n/a
Jtraderz |  | x
Mirabelle | x | x
CBS | x
TTS |  | x |  | x
Aller | x | x | x | x
Parfume.lv | x |  |  | x
Worksafety |  | x
BKI-VSP | x | x | x | x
CEF | x | x | x | x
LKN | x |  | x
Consul | x | x
Lori | n/a | n/a | n/a | n/a
CTC | x | x | x
Aller | x | x | x | x
Begonija | x | x | x | x
Jewel | n/a | n/a | n/a | n/a
X-Net |  | x
ACG |  | x |  | x
Alton |  |  | x
Baltikums | x | x | x | x
RigaRE | x |  | x
APFH | x |  | x
Saphir | x |  | x | x
Villa Blanca | x |  | x | x
Style-Sexy Shop |  | x
BBCorporate (Baltikums) | x | x | x | x